## Pranay Sprint
Goal Area | Layer | Parent Task | Sub Tasks | Key Deliverables | Sprint | Priority | Status | Start Date | Tentative End Date
Hakase Bio | Layer 1 — Molecular Digital Twin | Improve Go/Watch/No-Go scoring | Rebuilt scoring logic; added safety gates and confidence checks | More reliable, science-backed verdicts | Sprint 1 | High | Done
Hakase Bio | Layer 1 — Molecular Digital Twin | Novelty check & analogue data | Cross-check molecule across public databases; pull data from similar known compounds | Know if a molecule is novel or known + better estimates | Sprint 1 | High | Done
Hakase Bio | Layer 1 — Molecular Digital Twin | Benefit-risk assessment | Weigh safety against disease severity and unmet need using FDA data | Benefit-risk view alongside each verdict | Sprint 1 | High | Done
Hakase Bio | Layer 1 — Molecular Digital Twin | Connect trusted data sources | Wired in FDA, ChEMBL, Pharos, DailyMed and other databases | Verdicts backed by trusted external data | Sprint 1 | Medium | Done
Hakase Bio | Layer 1 — Molecular Digital Twin | ADMET accuracy & units | Show correct units; flag low-reliability predictions | Cleaner, more trustworthy ADMET outputs | Sprint 1 | Medium | Done
Hakase Bio | All layers | Dashboard redesign | New look, brand colours, light/dark mode, cleaner layout | Polished, professional dashboard | Sprint 1 | Medium | In Progress
Hakase Bio | Layers 1–3 | Layer handoff & sign-off | Pass outputs cleanly from Layer 1 to 2 to IVIVE to 3 with audit trail | Reliable, traceable stage handoffs | Sprint 1 | High | In Progress
Hakase Bio | Layers 1–3 | Next steps | Polish charts; recalibrate; extend data sources to Layers 2 & 3 | Further hardening | Sprint 2 | Medium | Backlog