## Hakase Sprint
Epic / Parent Task | Sub-task | Layer | Status | Priority | Notes / Source
Scoring engine — MPO + ICH gating | Geometric-mean desirability composite (Derringer-Suich/QED) | L1 | Done | P0 | One weak axis can't be averaged away
Scoring engine — MPO + ICH gating | Hard-veto gates grounded in ICH M7 / S7B / S2(R1) + Lipinski | L1 | Done | P0 | Thresholds cited in l1Thresholds.json
Scoring engine — MPO + ICH gating | Applicability-domain downgrade (out-of-domain -> WATCH) | L1 | Done | P0
Scoring engine — MPO + ICH gating | Conservative GO guard (no high-confidence GO on thin evidence) | L1 | Done | P1
Evidence & Novelty | Multi-DB novelty: PubChem + UniChem + Europe PMC | L1 | Done | P0 | noveltyResolver.ts
Evidence & Novelty | Fix PubChem CID-0 -> 'Novel — no public record' | L1 | Done | P0 | was mislabelled + broken link
Evidence & Novelty | Read-across from measured ChEMBL analogues (hERG/IC50) | L1 | Done | P0 | similarity ladder 70->55->40
Evidence & Novelty | Read-across coverage -> scorecard confidence | L1 | Done | P1
FDA Benefit-Risk layer | Five BRF dimensions (FDA 2023 guidance) | L1 | Done | P0 | benefitRisk.ts
FDA Benefit-Risk layer | openFDA severity / unmet-need (live, by indication) | L1 | Done | P0 | weighted 65-70% over prior
FDA Benefit-Risk layer | Pharos target validation -> benefit factor | L1 | Done | P0 | Tclin x1.08 ... Tdark x0.82
FDA Benefit-Risk layer | FDA boxed warning (openFDA label) -> risk | L1 | Done | P0 | favorable->borderline; molecule-specific
FDA Benefit-Risk layer | Safety veto sovereignty (hard liability never auto-GO) | L1 | Done | P0 | max CONDITIONAL -> committee
Trusted preclinical sources | NCATS Pharos proxy route (/api/preclinical/pharos) | L1 | Done | P0 | server-side; restart api-server
Trusted preclinical sources | DailyMed proxy route (/api/preclinical/dailymed) | L1 | Done | P0 | official FDA SPL; restart api-server
Trusted preclinical sources | Transparent 11-source registry | L1 | Done | P1 | PreclinicalEvidenceCard.tsx
ADMET correctness & units | Authoritative units from admet_ai admet.csv | L1 | Done | P0 | admetMeta.ts
ADMET correctness & units | Reliability flags; VDss/Half-Life marked unreliable (R2<0) | L1 | Done | P0
ADMET correctness & units | Fix wrong backend unit labels (Clearance/LD50/P-gp) | L1 | Done | P1 | admet_ml.py
HAIOps governance | Directional 'not a lab replacement' banner | L1 | Done | P0 | below verdict
Aesthetic revamp | Brand token system (panel/eyebrow/chip/glass/card) | All | Done | P1 | index.css
Aesthetic revamp | Direction A — Fraunces serif display headings | All | Done | P1
Aesthetic revamp | Direction B dark — airy editorial cards + verdict hero | All | Done | P1
Aesthetic revamp | De-purple -> Hakase cyan/teal (brand + primary tokens) | All | Done | P0
Aesthetic revamp | Backdrop depth + light-mode polish | All | Done | P1
Aesthetic revamp | Header cleanup: bigger logo, remove v1.0, remove hash chip | All | Done | P2
Aesthetic revamp | Retint radar/dose-response chart SVGs to teal | L1 | Backlog | P2 | last purple-ish bit
Aesthetic revamp | Full sidebar Direction-B sweep | L1 | Backlog | P2
Layer wiring / handoff | L1->L2->IVIVE->L3 evidence hash chain (output-driven) | L1-L3 | Verified | P0 | stage hash = prev hash + stage outputs
Layer wiring / handoff | IVIVE sign-off captured & folded into L3 audit trail | L2-L3 | Verified | P0
Layer wiring / handoff | Live RunPod L2 confirmation end-to-end | L2 | Needs live run | P1 | can't verify GPU backend from code
Next / backlog | Recalibrate L1 thresholds vs live ADMET-AI distribution | L1 | Backlog | P1 | recalibrate-l1-thresholds.mjs
Next / backlog | Caco-2 read-across + on-target IC50 by ChEMBL target id | L1 | Backlog | P2
Next / backlog | L2/L3 trusted sources (ClinicalTrials precedent, tox ref) | L2-L3 | Backlog | P1
Next / backlog | Surface ADMET reliability + benefit-risk in PDF report | L1 | Backlog | P2